## Sheet1
Action Item | Assigned To | Completion Date | Status | Comments
Git Repo Creation | Adarsh | 2022-07-07 | Completed | dwprepos / nb_healthcare — Bitbucket
API List Planning | Adarsh | 2022-07-08 | Completed
ReactJS Q&A Sample Page | Ravi | 2022-07-07 |  | Code will pushed to Git Repo
Middle Ware Authentication | Sandhya / Taruni | 2022-07-11
Serilog Implementation | Adarsh | 2022-07-11 | Completed
API Project Structure | Ravi | 2022-07-07 | Completed | Code will be pushed to Git Repo